## Project Plan
Year | Quarter | Week | Evironment | Continuous Integration | Continuous Delivery
2022 | Q2 | 2022-04-02 | Setup Azure environment and connect Azure Subscription with GitHub account Difficulty: 2 Time (h): 1 | Create GitHub repository for the project Difficulty: 2 Time (h): 1
|  | 2022-04-11 |  | Setup CI with GitHub actions Difficulty: 3 Time (h): 2
|  | 2022-04-18 | Develop IaC to deploy the infrastructure Difficulty: 4 Time (h): 8 | Test CI Difficulty: 3 Time (h): 3
|  | 2022-04-25 | Deploy and verify the infrastructure Difficulty: 3 Time (h): 4 |  | Setup Azure Devops pipline Difficulty: 3 Time (h): 3
|  | 2022-05-02 |  |  | Deploy application to app service using pipeline Difficulty: 2 Time (h): 8
|  | 2022-05-09 |  |  | Release for QA activities Difficulty: 2 Time (h): 2
|  | 2022-05-16 |  |  | Fix issue in QA's feedback Difficulty: 2 Time (h): 2
|  | 2022-05-23 |  |  | Full CI/CD demo Difficulty: 2 Time (h): 2
|  |  | Goals | Goals | Goals
|  |  | Have read to run Azure evivronment | Have automation testing using GitHub action | Provide CD for application using Azure Devops pipeline
Have reusable IaC